## QA RACI
QA PROCESS RACI Document
KEY:
| R | Responsible
| A | Accountable
| C | Consulted
| I | Informed
| Account Management | Project Management | UX | Creative | Strategic Analytics | Business Analyst | Dev Manager | Programmer | QA Manager | QA Analyst
Product Definition | R | A | C | C | C | A | C | I | I | I
Annotated Wireframes | C | A | R | C | I | C | C | C | I | I
Functional Specification | C | A | C | C | I | C | R | C | I | I
Dev/QA Kickoff | I | R | C | C | C | C | A | C | A | C
Create Test Plan | C | A | C | I | I | C | C | I | R | C
Review/Approve Test Plan | C | R | C | C | C | C | A | C | A | C
Update Test Plan | I | C | I | I | I | I | C | C | R | C
Write Test Cases | I | C | I | I | R | I | C | C | A | R
Review/Approve Test Cases | C | R | I | I | I | I | C | C | A | C
Update Test Cases | I | C | I | I | R | I | C | C | R | R
Execute Test Cases | I | A | I | R | R | I | C | C | A | R
Assign JIRA Tickets | C | A | C | C | C | C | A | A | R | I
Ticket Resolution | C | R | I | I | I | I | C | C | A | A
QA Certification | A | A | I | I | I | I | I | I | R | A
Product Definition | I C C: The Account Team is responsible for defining the product. PM's and BA's (if used on the project) will be accountable for their defined parts of the project.
Annotated Wireframes | I C C: UX will be responsible for creating and updating wireframes.
Functional Specification | I C C: Where UX writes the design document (The wires), Development is responsible for the Functional Specification Document.
The Development Manager will write the FD for the project, with the PM accountable for the completion of the task.
Dev/QA Kick-Off | I C C: The point where the Development Team and the QA Team starts to work on the project. The PM is responsible for the kick-off.
Create Test Plan | I C C: The test plan contains all relevant information for the testing effort. It is the QA Manager's responsibility to write the Test Plan.
The PM will be accountable that the Test Plan is completed.
Update Test Plan | I C C: The QA Manager is responsible for updating the Test Plan, with the PM and Dev's consulting so QA ensures all relevant updates are included in the plan.
Review/Approve Test Plan | I C C: The PM is responsible for Approving the Test Plan. Any changes to the Test Plan moving forward will need to be reviewed and approved by the PM.
Write Test Cases | I C C: There are different kinds of test cases, and therefore, different groups that are responsible for writing them.
The Strategic Analytics Team will write their own test cases. These cases will cover testing individual tags, reports, and other tracking cases.
The QA Team will be responsible for writing the System (Functional) test cases, Regression, and End-to-End cases as an example.
The PM, since they are approving the test cases, will be engaging the SA and Creative teams, asking them to create their own cases.
To assist in this effort, the QA Manager will include a template section in the Test Plan that addresses this.
Review/Approve Test Cases | I C C: The PM is accountable that each team has test cases (or at least a general plan) on what to test for the product.
Update Test Cases | I C C: Updates are to be made for the corresponding group that created them. The QA team updates Functional tests. The SA team updates tagging tests.
Execute Test Cases | I C C: Each Team is responsible for executing their test cases. PM keeps everyone accountable on progress of test case execution.
Assign JIRA Tickets | I C C: The teams are testing the product. Defect tickets are created - who should they be assigned to? QA.
All defect type tickets created in Jira should be first assigned to the QA Manager for initial ticket-triage. The QA Manager is responsible for examining the defect
and ensuring that all needed details for the issue have been entered - screenshots, steps, expected/actual results, etc…
With the QA Manager intercepting possible issue tickets early, we will be able to avoid sending non-issue tickets to the development team.
Note: Issues the QA Manager finds will be assigned to either the PM or the Dev Manager on the project, whichever is appropriate.
Ticket Resolution | I C C: The PM is responsible that the ticket is resolved before the project can pass testing. The development team consults with the PM's and the QA team is responsible
in seeing that the tickets are visible to the PM.
QA Certification | I C C: The QA team is responsible for Certifying the build as Passed Testing. The PM and Account team is accountable that the certification is provided
before the product is released into Production/Live environment.