## Sheet1
Risk Management Assessment Report
# | Risk Description | Methodology | Resource | Live Date | BT Dependency | BT Resource | External Dependency | Severity (1-10) X | Probability (1-10) = | Risk Level (1-100)
| Project Name: Q4/Shop D Facebook App | Waterfall | Devin | 2013-11-19 | None | N/A | Facebook
1 | Fidelity and accuracy of recommendation engine – if any changes post code freeze, incremental changes. | [8 empty] | 0
2 | Reliance on Facebook API and friends permissions could affect quality of recommendations | [8 empty] | 0
3 | Building internal tech requirements doc – changes downstream | [8 empty] | 0
4 | Devin overtasked | [8 empty] | 0
5 | Chris v. availability – need his oversight/help and he’s been unavailable | [8 empty] | 0
6 | Could use another FE resource to focus on mobile experience | [8 empty] | 0
7 | Need domain decision/SSL Purchase – posted to attask | [8 empty] | 0
8 | Timing to get to Dev Mgr review seems aggressive given gut check of where we are today. 2 weeks from today. | [8 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0