## QA RACI
QA PROCESS RACI Document
KEY:
| R | Responsible | The person responsible is the person who does the task.
| A | Accountable | The accountable person makes sure the responsible person does the task.
| C | Consultant | The consulted person collaborates with the responsible person on the task
| I | Informed | The informed person is informed when the the task is done
| Account Management | Project Management | UX | Creative | Strategic Analytics | Business Analyst | Dev Manager | Developer | QA Manager | QA Analyst
Product Definition | R | A | C | C | C | A | C | I | I | I
Annotated Wireframes | C | A | R | C | I | C | C | C | I | I
Business Specification (BRD) | A | C | C | C | C | R | C | C | I | I
Functional Specification (FSD) | C | A | C | C | I | C | R | C | I | I
Dev/QA Kickoff | C | R | I | I | I | I | A | C | C | C
Create Test Plan | C | A | C | C | I | C | C | C | R | C
Review/Approve Test Plan | A | R | C | C | C | C | A | C | C | C
Create GA Tagging Plan | C | A | I | C | R | C | C | I | I | I
Update Test Plan | I | A | I | I | I | I | C | C | R | C
Write Test Cases | I | C | I | I | I | I | C | C | A | R
Review/Approve Test Cases | C | C | I | I | I | I | C | C | A | R
Update Test Cases | I | C | I | I | I | I | C | C | A | R
Execute Test Cases | I | C | I | I | I | I | C | C | A | R
Assign JIRA Tickets | C | C | I | I | I | I | C | C | A | R
Ticket Resolution | C | R | I | I | I | I | A | C | C | C
Ticket Retesting | C | C | I | I | I | I | C | C | A | R
QA Certification | C | C | I | I | I | I | I | I | A | R
Product Definition | C I I C I I C C C C: The Account Team is responsible for defining the product. PM's and/or BA's (if used on the project) will be accountable for their defined parts of the project.
Annotated Wireframes | C I I C I I C C C C: UX will be responsible for creating and updating wireframes.
Business Specification | C I I C I I C C C C: The Business Analyst creates this document (Business Requirements Document).
Functional Specification | C I I C I I C C C C: Where UX writes the design document (The wires), Development is responsible for the Functional Specification Document.
The Development Manager will write the FD for the project, with the PM accountable for the completion of the task.
Dev/QA Kick-Off | C I I C I I C C C C: The point where the Development Team and the QA Team starts to work on the project. The PM is responsible for the kick-off.
Create Test Plan | C I I C I I C C C C: The test plan contains all relevant information for the testing effort. It is the QA Manager's responsibility to write the Test Plan.
The PM will be accountable that the Test Plan is completed.
Review/Approve Test Plan | C I I C I I C C C C: The PM is responsible for Approving the Test Plan. Any changes to the Test Plan moving forward will need to be reviewed and approved by the PM.
Ideally the Account Manager, Project Manager and Dev manager all approve the test plan.
Create GA Tagging Plan | C I I C I I C C C C: The Strategic Analytics Analyst creates and manages this plan which includes testing tagging/tracking the project.
Update Test Plan | C I I C I I C C C C: The QA Manager is responsible for updating the Test Plan, with the PM and Dev's consulting so QA ensures all relevant updates are included in the plan.
Write Test Cases | C I I C I I C C C C: The QA Team will be responsible for writing the System (Functional) test cases, Regression, and End-to-End cases.
Review/Approve Test Cases | C I I C I I C C C C: The PM is accountable that each team has test cases (or at least a general plan) on what to test for the product.
Update Test Cases | C I I C I I C C C C: Updates are to be made for the corresponding group that created them. The QA team updates Functional tests. The SA team updates tagging tests.
Execute Test Cases | C I I C I I C C C C: Each Team is responsible for executing their test cases. PM keeps everyone accountable on progress of test case execution.
Assign JIRA Tickets | C I I C I I C C C C: The teams are testing the product. Defect tickets are created - who should they be assigned to? QA.
All defect type tickets created in Jira should be first assigned to the QA Manager for initial ticket-triage. The QA Manager is responsible for examining the defect
and ensuring that all needed details for the issue have been entered - screenshots, steps, expected/actual results, etc…
With the QA Manager intercepting possible issue tickets early, we will be able to avoid sending non-issue tickets to the development team.
Note: Issues the QA Manager finds will be assigned to either the PM or the Dev Manager on the project, whichever is appropriate.
Ticket Resolution | C I I C I I C C C C: The Project Manager (in most cases) is responsible that the ticket is resolved before the project can pass testing. The Dev manager will follow-up with the PM.
QA IS NOT RESPONSIBLE FOR ENSURING ALL DEFECTS ARE RESOLVED. PM and or Account owns this and they own the project.
Ticket Retesting | C I I C I I C C C C: Anyone who creates a ticket should be inn theory the one that retests to ensure that the fix is correct. 99% of the time this is the QA Analyst.
QA Certification | C I I C I I C C C C: The QA team is responsible for Certifying the build as Passed Testing. Ideally, the certificate is issued BEFORE the project is delivered to the client.
QA will certify that all tickets are resolved/closed and all exit/acceptance creitera are met.